## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | Design Welcome Page UI | Must | None | UI Team | Completed
1 | 1 | US-002 | Display Basic Bank Features | Must | None | UI Team | Completed
1 | 1 | US-003 | Create CTA Button | Must | None | UI Team | Completed
1 | 1 | US-004 | Build About/Privacy Modal | Should | None | UI Team | Completed
1 | 1 | US-005 | Implement Animations & Counters | Could | US-001 | UI Team | Completed
1 | 1 | US-006 | Create Login Page UI | Must | None | UI Team | Completed
1 | 1 | US-007 | Login Authentication Backend | Must | US-006 | Backend Team | Completed
1 | 1 | US-008 | Forgot Password Flow | Should | US-007 | Backend Team | Completed
1 | 1 | US-009 | OTP Verification | Must | US-007 | Backend Team | Completed
1 | 1 | US-010 | Session Management & Logout | Must | US-007 | Backend Team | Completed
2 | 2 | US-011 | Customer Dashboard UI | Must | US-006 | UI Team | Completed
2 | 2 | US-012 | Balance Summary Card | Must | US-011 | Backend/UI | Completed
2 | 2 | US-013 | Last Login & IP Info | Should | US-007 | Backend Team | Completed
2 | 2 | US-014 | Account Age Display | Could | None | Backend Team | Completed
2 | 2 | US-015 | Policies Modal | Could | None | UI Team | Completed
2 | 2 | US-016 | Floating AI Chatbot | Should | US-011 | AI Team | Completed
3 | 3 | US-017 | View Account Details Page | Must | US-012 | Fullstack Team | Completed
3 | 3 | US-018 | Balance History Graph | Should | US-017 | UI Team | Completed
3 | 3 | US-019 | Money Transfer | Must | US-017 | Backend Team | Completed
3 | 3 | US-020 | Withdraw Money | Should | US-019 | Backend Team | Completed
3 | 3 | US-021 | Deposit Money | Should | US-017 | Backend Team | Completed
3 | 3 | US-022 | Statement Download | Could | US-017 | Backend Team | Completed
3 | 3 | US-023 | Set Daily Limit | Could | US-017 | Backend Team | Completed
3 | 3 | US-024 | Freeze/Unfreeze Card | Must | US-017 | Backend Team | Completed
3 | 3 | US-025 | Virtual Debit Card | Must | US-017 | Fullstack | Completed
4 | 4 | US-026 | Loan Application UI | Must | US-017 | UI Team | Completed
4 | 4 | US-027 | Loan History | Should | US-026 | Fullstack Team | Completed
4 | 4 | US-028 | Raise Complaint | Must | None | Fullstack Team | Completed
4 | 4 | US-029 | Complaint History | Should | US-028 | UI Team | Completed
4 | 4 | US-030 | Credit Score API | Could | External API | Backend Team | Completed
4 | 4 | US-031 | Expense Analysis Charts | Could | US-012 | UI Team | Completed
4 | 4 | US-032 | Change PIN | Must | US-017 | Backend Team | Completed
4 | 4 | US-033 | Recharge/Bill Payment | Could | External API | Backend Team | Completed
4 | 4 | US-034 | Delete Account Request | Should | US-017 | Backend Team | Completed
5 | 5 | US-035 | Admin Login UI | Must | None | UI Team | Completed
5 | 5 | US-036 | Admin Dashboard UI | Must | US-035 | UI Team | Completed
5 | 5 | US-037 | Admin Last Login/IP | Should | US-035 | Backend Team | Completed
5 | 5 | US-038 | Summary Stats Cards | Must | US-036 | Fullstack Team | Completed
5 | 5 | US-039 | View All Accounts | Must | US-038 | Backend Team | Completed
5 | 5 | US-040 | View Transactions | Must | US-038 | Backend Team | Completed
5 | 5 | US-041 | View Complaints | Should | US-028 | Backend Team | Completed
5 | 5 | US-042 | Freeze/Unfreeze Account | Must | US-039 | Backend Team | Completed
5 | 5 | US-043 | Generate Reports | Should | US-039 | Backend Team | Completed
5 | 5 | US-044 | Approve Loan Requests | Should | US-026 | Backend Team | Completed
5 | 5 | US-045 | View System Logs | Could | None | Backend Team | Completed
5 | 5 | US-046 | Activity Heatmap | Could | US-038 | Analytics Team | Completed
5 | 5 | US-047 | Rollback/Refund Requests | Should | US-040 | Backend Team | Completed
5 | 5 | US-048 | Send Notice | Should | None | Admin Team | Completed
5 | 5 | US-049 | Analytics Dashboard | Could | US-038 | Data Team | Completed
5 | 5 | US-050 | Approve/Delete Account Requests | Should | US-034 | Backend Team | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 320 | 50 | 50 | 49 | 43 | 43 | 20 | 20 | 20 | 5 | 5 | 5 | 5 | 5 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Design Welcome Page UI | 15-Oct-2025 | 28-Oct-2025 | UI Team | Frontend | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-002 | Display Basic Bank Features | 15-Oct-2025 | 28-Oct-2025 | UI Team | Frontend | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-003 | Create CTA Button | 15-Oct-2025 | 28-Oct-2025 | UI Team | Frontend | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-004 | Build About/Privacy Modal | 15-Oct-2025 | 28-Oct-2025 | UI Team | Frontend | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-005 | Implement Animations & Counters | 15-Oct-2025 | 28-Oct-2025 | UI Team | Animation | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-006 | Create Login Page UI | 15-Oct-2025 | 28-Oct-2025 | UI Team | Frontend | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-007 | Login Authentication Backend | 15-Oct-2025 | 28-Oct-2025 | Backend Team | API/Security | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-008 | Forgot Password Flow | 15-Oct-2025 | 28-Oct-2025 | Backend Team | API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-009 | OTP Verification | 15-Oct-2025 | 28-Oct-2025 | Backend Team | Security | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-010 | Session Management & Logout | 15-Oct-2025 | 28-Oct-2025 | Backend Team | Security | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-011 | Customer Dashboard UI | 29-Oct-2025 | 11-Nov-2025 | UI Team | Frontend | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-012 | Balance Summary Card | 29-Oct-2025 | 11-Nov-2025 | Backend/UI | Fullstack | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-013 | Last Login & IP Info | 29-Oct-2025 | 11-Nov-2025 | Backend Team | Security | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-014 | Account Age Display | 29-Oct-2025 | 11-Nov-2025 | Backend Team | API | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-015 | Policies Modal | 29-Oct-2025 | 11-Nov-2025 | UI Team | Frontend | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-016 | Floating AI Chatbot | 29-Oct-2025 | 11-Nov-2025 | AI Team | AI Integration | Completed | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-017 | T-017 | View Account Details Page | 12-Nov-2025 | 25-Nov-2025 | Fullstack Team | Fullstack | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | T-018 | Balance History Graph | 12-Nov-2025 | 25-Nov-2025 | UI Team | Charts | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | T-019 | Money Transfer | 12-Nov-2025 | 25-Nov-2025 | Backend Team | API | Completed | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-020 | T-020 | Withdraw Money | 12-Nov-2025 | 25-Nov-2025 | Backend Team | API | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T-021 | Deposit Money | 12-Nov-2025 | 25-Nov-2025 | Backend Team | API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | T-022 | Statement Download | 12-Nov-2025 | 25-Nov-2025 | Backend Team | File Generation | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | T-023 | Set Daily Limit | 12-Nov-2025 | 25-Nov-2025 | Backend Team | API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | T-024 | Freeze/Unfreeze Card | 12-Nov-2025 | 25-Nov-2025 | Backend Team | Security | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-025 | T-025 | Virtual Debit Card | 12-Nov-2025 | 25-Nov-2025 | Fullstack | UI/Security | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-026 | T-026 | Loan Application UI | 12-Nov-2025 | 25-Nov-2025 | UI Team | Frontend | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-027 | T-027 | Loan History | 12-Nov-2025 | 25-Nov-2025 | Fullstack Team | Fullstack | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-028 | T-028 | Raise Complaint | 12-Nov-2025 | 25-Nov-2025 | Fullstack Team | Fullstack | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-029 | T-029 | Complaint History | 12-Nov-2025 | 25-Nov-2025 | UI Team | Frontend | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-030 | T-030 | Credit Score API | 12-Nov-2025 | 25-Nov-2025 | Backend Team | Integration | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-031 | T-031 | Expense Analysis Charts | 12-Nov-2025 | 25-Nov-2025 | UI Team | Analytics | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-032 | T-032 | Change PIN | 12-Nov-2025 | 25-Nov-2025 | Backend Team | Security | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-033 | T-033 | Recharge/Bill Payment | 12-Nov-2025 | 25-Nov-2025 | Backend Team | Integration | Completed | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-034 | T-034 | Delete Account Request | 12-Nov-2025 | 25-Nov-2025 | Backend Team | API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-035 | T-035 | Admin Login UI | 26-Nov-2025 | 06-Dec-2025 | UI Team | Frontend | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-036 | T-036 | Admin Dashboard UI | 26-Nov-2025 | 06-Dec-2025 | UI Team | Frontend | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-037 | T-037 | Admin Last Login/IP | 26-Nov-2025 | 06-Dec-2025 | Backend Team | Security | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-038 | T-038 | Summary Stats Cards | 26-Nov-2025 | 06-Dec-2025 | Fullstack Team | Fullstack | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-039 | T-039 | View All Accounts | 26-Nov-2025 | 06-Dec-2025 | Backend Team | API | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-040 | T-040 | View Transactions | 26-Nov-2025 | 06-Dec-2025 | Backend Team | API | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-041 | T-041 | View Complaints | 26-Nov-2025 | 06-Dec-2025 | Backend Team | API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-042 | T-042 | Freeze/Unfreeze Account | 26-Nov-2025 | 06-Dec-2025 | Backend Team | Security | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-043 | T-043 | Generate Reports | 26-Nov-2025 | 06-Dec-2025 | Backend Team | File System | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-044 | T-044 | Approve Loan Requests | 26-Nov-2025 | 06-Dec-2025 | Backend Team | API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-045 | T-045 | View System Logs | 26-Nov-2025 | 06-Dec-2025 | Backend Team | Logging | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-046 | T-046 | Activity Heatmap | 26-Nov-2025 | 06-Dec-2025 | Analytics Team | Analytics | Completed | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-047 | T-047 | Rollback/Refund Requests | 26-Nov-2025 | 06-Dec-2025 | Backend Team | Transactions | Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-048 | T-048 | Send Notice | 26-Nov-2025 | 06-Dec-2025 | Admin Team | UI/API | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-049 | T-049 | Analytics Dashboard | 26-Nov-2025 | 06-Dec-2025 | Data Team | Analytics | Completed | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-050 | T-050 | Approve/Delete Account Requests | 26-Nov-2025 | 06-Dec-2025 | Backend Team | Workflow | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | Login API not connecting to DB | DB credentials updated, service restarted
1 | 2 | UI alignment issue in Login Page | CSS fixes applied, QA re-tested
1 | 3 | OTP SMS not delivered | Switched to fallback SMS provider
1 | 4 | Session timeout occurring too early | Increased timeout from 5 to 15 minutes
1 | 5 | Build pipeline failure | Jenkins config corrected, build triggered
1 | 6 | Auth API responding slowly | Enabled caching, improved latency
1 | 7 | UI team waiting for API contract | API schema shared with UI team
1 | 8 | Animation lag on home page | Optimized images and removed unused JS
1 | 9 | DB migration script failed | Missing column added, migration re-executed
1 | 10 | Incorrect validation on reset form | Added server-side validation
1 | 11 | Backend logs growing too fast | Enabled log rotation
1 | 12 | SMS provider outage | Switched to backup gateway
1 | 13 | QA lacking test data | Created and shared sample dataset
1 | 14 | Minor UI bugs pending | Fixed and re-tested

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 15-Oct-2025 | 28-Oct-2025 | Jambava,Rithikaa,Soumya | Start writing unit tests early | Stop pushing code without review | Continue daily standups | Implemented pre-commit review checks
2 | 2 | 29-Oct-2025 | 11-Nov-2025 | Jambava,Rithikaa,Soumya | Start component reusability | Stop redesigning without requirement | Continue clean coding | Created UI component library
3 | 3 | 12-Nov-2025 | 25-Nov-2025 | Jambava,Rithikaa,Soumya | Start documenting APIs | Stop delaying bug fixes | Continue API versioning | Added Swagger documentation
4 | 4 | 26-Nov-2025 | 06-Dec-2025 | Jambava,Rithikaa,Soumya | Start automation scripts | Stop repetitive manual testing | Continue structured test cases | Started Cypress automation suite
5 | 5 | 26-Nov-2025 | 06-Dec-2025 | Jambava,Rithikaa,Soumya | Start monitoring alerts | Stop ignoring build warnings | Continue CI/CD improvements | Enhanced Jenkins pipeline rules